## Proc Plan Template
ZOMBA CITY COUNCIL
Annual Procurement Plan
2023-2024
Last Updated:1/04/2023 |  | {date updated}
Serial No. | Type/Nature of Procurement | Procurement Description | Budgeted Amount | Procurement Method | Supplier Target Group | Planned Date of initiating the Process | Planned Date of Delivery/ Completion
1 | Works | Upgrading of Namiwawa Road (Dualisation) | 560000000 | Open Tender | Other | 24th July, 2021 | 30th October, 2023
2 | Works | Upgrading of Namiwawa Road Extension (SRWB Junction )-Mpunga Market (Asphalt Overlay) | 680000000 | Open Tender | Other | 24th July, 2021 | 30th October, 2023
3 | Works | Construction of Sadzi THA Road to Last Night | 400000000 | Open Tender | Other | 24th July, 2021 | 30th October, 2023
4 | Works | Upgrading of Kalimbuka Ring Road | 800000000 | Open Tender | Other | 24th July, 2021 | 30th October, 2023
5 | Works | Upgrading of Mpoto Road (Thundu Road) | 760000000 | Open Tender | Other | 24th July, 2021 | 30th October, 2023
6 | Works | Upgrading of Sogoja Road | 1, 363, 715, 490.00 | Open Tender | Other | 24th July, 2021 | 30th October, 2023
7 | Consultancy Services | Design Review and Construction Supervision of Various Roads in Zomba City | 130000000 | Open Tender | Other | 24th July, 2021 | 30th October, 2023
8 | Consultancy Services | Production of Detailed Engineering Designs, Design Review and Construction Supervision of Various Roads in Zomba City | 0 | Open Tender | Other | 24th July, 2021 | 30th October, 2023
1 | Works | Construction of Namphambo Bridge | 469063787.5 | Open Tender | Other | 14th April 2022 | 30th December, 2023
2 | Works | Rehabilitation of Ndola Roads | 815500770 | Open Tender | Other | 14th April, 2022 | 30th December, 2023
3 | Works | Supply delivery and installation of concrete poles | 188763750 | Open Tender | Other | 14th April, 2022 | 30th December, 2023
4 | Works | Supply delivery and installation of Solar streetlights | 359,075,000 .00 | Open Tender | Other | 14th April, 2022 | 30th December, 2023
5 | Works | Upgrading of Chinamwali-Ndelemani Road | 980904125 | Open Tender | Other | 14th April, 2022 | 30th December, 2023
6 | Works | Construction of Shops under DFLA Projects
a | Works | Flea Market Shops | 204, 016, 347.27. | Open Tender | Other | 14th April, 2022 | 31st December, 2023
b | Works | Namiwawa Shops Opposite Shoprite | 424, 759, 399.25. | Open Tender | Other | 14th April, 2022 | 31st December, 2023
c | Works | Bus Depot Shops | 281104455.85 | Open Tender | Other | 14th April, 2022 | 31st December, 2023
| Works | CITY ROADS
1 | Works | Old-Naisi-Malonje-Habitat- Road | 533333333 | Open Tender | Other | 2nd January, 2024 | 30th September, 2024
2 | Works | Masache-Satema -Mtiya Road | 533333333 | Open Tender | Other | 2nd January, 2024 | 30th September, 2024
3 | Works | Off Namiwawa-Sewerage Road | 533333333 | Open Tender | Other | 2nd January, 2024 | 30th September, 2024
4 | Works | Chirunga-Mpoto-Matawale Road | 533333333 | Open Tender | Other | 2nd January, 2024 | 30th September, 2024
5 | Works | Chejusi-Masongola road | 533333333 | Open Tender | Other | 2nd January, 2024 | 30th September, 2024
6 | Works | Sadzi-Chikowi-Mpunga Road | 533333333 | Open Tender | Other | 2nd January, 2024 | 30th September, 2024
7 | Works | Road Maintenance | 200000000 | Open Tender | Other | 24th May, 2023 | 30th September, 2023
8 | Consultancy Services | Consultancy Services for RFA and City Roads Treasury Fund | - | Open Tender | Other | 2nd January, 2024 | 30th October, 2023
| Works and Goods | WATER FUND PROJECTS
9 | Works | For Construction of various water Kiosks | 12000000 | Request for Quotations | MSMEs | 20th June, 2023 | 20th July,2023
| Goods and Works | CDF PROJECTS
10 | Works | For various Projects | 85000000 | Request for Quotations | MSMEs | 20th June, 2023 | 20th July,2023
| Works | IDF PROJECTS
| Works | For various Projects | 103000 | Request for Quotations | MSMEs | 20th June, 2023 | 20th July,2023
7 | Works | Locally Generated Revenue Projects
8 | Works | (a) Road rehabilitation(Gravelling, Grading, pothole patching) | 7500000 | Request for Quotations | MSMEs | 14th April 2022 | 30th July, 2023
9 | Works | (b) Maintenance of Council uilding | 15000000 | Request for Quotations | MSMEs | 14th April 2022 | 30th July, 2023
10 | Works | ( c) Maintenance of Streetlights) | 7500000 | Request for Quotations | MSMEs | 14th April 2022 | 30th July, 2023
11 | Works | (d) Rehabilitation of Zomba Civic Offices | 22500000 | Request for Quotations | MSMEs | 14th April 2022 | 30th July, 2023
14 | Consultancy Services | Provision of Legal Services | 4000000 | Open Tender | Other | 24th May, 2023 | 30th July, 2023
17 | Goods | Supply and Delivery of Stationery | 33008559.7215 | Open Tender | MSMEs | 24th May, 2023 | 30th July, 2023
18 | Services | Provision of Security Services | 33408000 | Open Tender | Other | 24th May, 2023 | 30th July, 2023
19 | Goods | Supply and Delivery of Consumables | 23377769.349 | Open Tender | MSMEs | 24th May, 2023 | 30th July, 2023
20 | Goods | Supply and Delivery of Motor Vehicle Tyres and Lubricants | 63216000 | Open Tender | MSMEs | 24th May, 2023 | 30th July, 2023
21 | Goods | Uniform and Protective Cloth | 9883500 | Request for Quotations | MSMEs | 24th May, 2023 | 30th July, 2023
22 | Goods | Plant, furniture and office Equipment | 4869700 | Request for Quotations | MSMEs | 24th May, 2023 | 30th July, 2023
23 | Services | Maintenance of Motor vehicle | 18376953.975 | Request for Quotations | MSMEs | 24th May, 2023 | 30th July, 2023
24 | Goods | Procurement of Two Motor Vehicle | 95000000 | Open Tender | Other | 24th May, 2023 | 30th September, 2023
|  | TOTAL | 9900080369.3955
| Summary |  | Sub-Total Amount | Percentage of Total Value (%)
|  | MSME | 302335483.0455 | 3.054%
|  | Others | 9597744886.35 | 96.95%
Prepared by: Name: Yamikani Chinjala Position: Principal Procurement Officer Signature:…………………………….Date:15/04/2023
Reviewed by IPDC Chairman: Name: Philmon Maseko Signature:…………………………….Date: 15/04/2023
Approved by Head of PDE: Name: Fred Nankuyu Signature:…………………………….Date: 15/04/2023
Key:
Type/Nature refers to Goods/Works/Services
Procurement Details refer to what actually is to be procured e.g. stationery or motor vehicle
The information given is for planning purposes and is subject to revision or cancellation. It does not constitute a final commitment to buy the goods and services until the procurement process is initiated
PDEs are encouraged to prepare detailed plans for each contract to help in monitoring progress
Supplier Target Group is either MSME and Other which is not MSME
Note: The plan may be updated at the earliest after six months